## Sheet1
CMPE 352 Spring 2015 Group 1 - Responsibility Assignment Matrix
R - RESPONSIBLE A - ACCOUNTABLE C - CONSULTED I - INFORMED | Group Members | [10 empty] | Assessors
Task Name | Harun Acar | Çağla Balçık | Arda Çınar | Mustafa Efendioğlu | Onur Güler | Alp Hekimoğlu | Onur Musaoğlu | Görkem Önder | Pınar Sığın | Mert Tiftikçi | Mehmet Alper Yayıkçı | Can Tunca | Alp Kındıroğlu | Suzan Üsküdarlı
Research
Android Application Development Research | I | R | I | I | R | I | I | I | I | R | R | C
Semantic Tagging Research | R | I | R | I | I | I | I | I | R | I | I |  |  | I
Crowdsourcing Research | I | I | I | R | I | R | R | R | I | I | I |  | I
Documents
Requirements Analysis | I | I | I | I | I | I | I | R | R | R | I |  |  | I
Domain Anaysis | I | I | I | R | R | I | R | I | I | I | R | C | C
User Stories | R | R | R | R | R | R | R | R | R | R | R
User Cases | R | R | R | R | R | R | R | R | R | R | R |  |  | C
Scenarios | R | R | R | R | R | R | R | R | R | R | R
Mockups
Web Mockup | R | I | I | I | I | I | I | R | R | I | I
Mobile Mockup | R | I | I | I | I | I | I | R | R | I | I
Diagrams
Class Diagram | R | I | I | I | R | I | R | R | I | I | I | C | I | C
Sequence Diagram | R | R | R | R | R | R | R | R | R | R | R
Test Cases | R | R | R | R | R | R | R | R | R | R | R |  | C
Review of Project | R | R | R | R | R | R | R | R | R | R | R | I
System Design
Database Schema Design
Design of Genereal Code Structure
Design of Submodule Interface
Development
User Management
Ingredient Subsystem
Recipe Subsystem
Connecting Users and Recipes
Comment/Like(User-Recipe Interaction)
Moderation System
Subsystem Testing
Documentation
System Testing/Bugfixing
System Configuration
Deployment